Red House-Programme of Enabling Works

MONTH 1

• Plot 1 – Pre-Start & Groundworks Setup

Mobilisation, welfare, hoarding, groundworks establishment.

• Plot 2 – Pre-Start & Groundworks Setup

Start permitted, but operations run approximately two weeks behind Plot 1 to comply with staggered phasing.

• Red House – Site Preparation & Protection Works

Cleaning, clearance, protective measures.

MONTH 2

• Plot 1 – Foundations Preparation.

• Plot 2 – Foundations Preparation.

• Red House – Internal Strip-Out & Temporary Works

MONTH 3

• Plot 1 – Ground Floor Build-Up, Slab & Drainage

• Plot 2 – Ground Floor Build-Up, Slab & drainage

Sequenced 2–3 weeks behind Plot 1 to allow lead times and staggered deliveries/phasing

• Red House – Structural Masonry Repairs

Wall stitching, structural integrity improvements.

MONTH 4

• Plot 1 – Timber Frame Erection

• Plot 2 – Drainage / schedule spacing

Scheduled to avoid crane overlap and maintain staggered delivery.

• Red House – Roof structure & Structural Reinforcement

MONTH 5

• Plot 1 – Roof Structure & Weatherproof Shell

• Plot 2 – Timber Frame Erection

May proceed only once Plot 2 sale is authorised.

• Red House – External Envelope Works (incl. New Windows)

External repairs, masonry works, chimney, and installation of new windows.

Programme reassessment for a new programme to continue on completion of plot 2

MONTH 6

• Plot 1 – External Envelope Brickwork & Facades

• Plot 2 – Roof Structure & Weatherproof Shell

May advance only if Red House Month 5 milestone is achieved and authorised.

MONTH 7

• Plot 1 – First Fix M&E and Underfloor Heating

• Plot 2 – External Envelope Brickwork

MONTH 8

• Plot 1 – Screeds, Plasterboard & Airtightness

• Plot 2 – First Fix M&E and Underfloor Heating

MONTH 9

• Plot 1 – Plastering & External Finishes

• Plot 2 – Screeds & Plasterboard

MONTH 10

• Plot 1 – Second Fix M&E & Carpentry

• Plot 2 – Plastering & External Finishes

MONTH 11

• Plot 1 – Decoration, Flooring & Final Fix

• Plot 2 – Second Fix M&E & Carpentry

MONTH 12

• Plot 1 – External Works & Practical Completion

• Plot 2 – Decoration & Final Fix

MONTH 13

• Plot 2 – External Works

Begins after Plot 1 handover and planning confirmation.

MONTH 14

• Plot 2 – Practical Completion & Handover

Following the completion and sale of Plot 2, internal refurbishment and fit-out works to the Red House will continue beyond the current programme. These works will progress under a separate internal works package, sequenced to commence once Plot 2 handover and associated planning obligations have been discharged.

Jordan Howe on Behalf of Howe Rigout and Construction